## Sheet1
Work Item Type | Title1 (Epic) | Title 2 (User story/Task) | Title 3 | Estimate
Epic | PTMS - Public Transportation Managment System
Epic | User Managment
User story |  | User Registration and authentication |  | 5
Task |  |  | Design authentication flow
Task |  |  | Implement role-based access control
Test case |  |  | Verify secure login and access
Epic | Passenger services |  | Account lock after multiple failed logins
Password reset and email verification
User profile update
User Story |  | Real-time schedule visualization |  | 5
Task |  |  | Integrate live vehicle data
Test case |  |  | Validate real-time updates
Handle service disruption notifications
Optimize refresh rate for performance
Epic | Vehicle tracking |  | Filter schedules by line and stop
User story |  | Vehicle tracking on map |  | 5
Refresh vehicle positions in real time
Show vehicle direction and speed
Task |  |  | Map and GPS integration
Test case |  |  | Verify vehicle position accuracy
Epic | NFC Passenger Registration |  | Fallback behaviour when GPS signal is lost
User story |  | NFC-based passenger registration |  | 8
Sync offline NFC records when reconnected
Store entry/exit timestamps
Task |  |  | Implement IoT - NFC communication
Test case |  |  | Verify encrypted NFC communication
Epic | Operator Managment |  | Handle duplicated or failed NFC scans
User story |  | Route, stop and service managment |  | 5
Publish extraordinary traffic notifications
Versioning of routes and schedules
Task |  |  | CRUD (create,read, update, delete) routes and stops
Test case |  |  | Validate route changes
Epic | Reporting and Statistics |  | Assign vehicles to routes
User story |  | Passenger reporting and statistics |  | 5
View reported incidents on map
Export statistics reports (PDF/CSV)
Task |  |  | Implement reporting module
Test case |  |  | verify reports and statistics
Aggregate usage statistics per line
Epic | non-funcional Requirements |  | Aggregate statistics per time period
User story |  | Security and performance compliance |  | 8
Monitor system availability (99.5%)
Task |  |  | Encrypt all communication channels
Test case |  |  | Validate performance <500ms
Scalability testing under load